## WBS
Recognition WBS
Current state | Packet Constitution Option A export + verify is green directly. Remaining work is to make the runner/install path clean, deterministic, and free of false success banners.
ID | Task | Owner | Start | Due | Status | Dependencies | Notes | %Complete
1.0 | Program management and spec lock |  |  |  | In Progress |  | Recognition scope locked: standalone Windows-first browser with Packet Constitution export law; fill dates/owners. | 55%
1.1 | Finalize Recognition product spec |  |  |  | In Progress |  | Browser to spec: privacy-first, standalone, WebView2-based, exportable, governed, deterministic evidence artifacts. | 70%
1.2 | Lock DoD and release gates |  |  |  | In Progress | 1.1 | DoD includes export+verify green, deterministic packet selftest green, and reproducible packaging/install. | 50%
1.3 | Maintain canonical roadmap / change log |  |  |  | Not Started | 1.1 |  | 0%
2.0 | Packet Constitution Option A core |  |  |  | In Progress |  | Current critical path. | 70%
2.1 | Repair _lib_packet_constitution_v1.ps1 |  |  |  | In Progress |  | Remaining blocker: stable green run without manual patch drift. | 85%
2.2 | Stabilize pc_build_packet_optionA_v1.ps1 |  |  |  | In Progress | 2.1 | Builder parses; copy and deterministic hashing logic repaired iteratively. | 80%
2.3 | Stabilize pc_verify_packet_optionA_v1.ps1 |  |  |  | Done | 2.1 | Verify script parses and has passed direct export verification. | 100%
2.4 | Green _selftest_packet_constitution_v1.ps1 end-to-end |  |  |  | In Progress | 2.1,2.2,2.3 | Selftest is very close; final packet-id consistency and runner hygiene were active issues. | 85%
2.5 | Keep PacketId deterministic |  |  |  | In Progress | 2.1,2.2 | Manifest has no timestamp; hash must be computed over canonical LF-normalized bytes with trailing LF. | 90%
3.0 | Recognition export law |  |  |  | In Progress |  | Export law is the immediate milestone. | 80%
3.1 | Green recognition_export_session_packet_v1.ps1 |  |  |  | Done | 2.2,2.3 | Export + verify went green directly against packets/outbox. | 100%
3.2 | Default payload/session_export workflow |  |  |  | In Progress | 3.1 | Exporter now handles default paths; final runner still needs to be made clean. | 75%
3.3 | Operator runner / patch hygiene |  |  |  | In Progress | 2.1 | Need one clean no-false-green runner that rewrites scripts deterministically in a child PowerShell process. | 60%
4.0 | Trust / receipts / evidence chain |  |  |  | Not Started |  | Post-export-law hardening. | 5%
4.1 | NeverLost receipts NDJSON integration |  |  |  | Not Started | 2.0 | Emit deterministic receipts for export / verify / trust changes. | 0%
4.2 | Allowed signers / trust bundle derivation |  |  |  | Not Started | 4.1 |  | 0%
4.3 | WatchTower verification compatibility |  |  |  | Not Started | 4.1,4.2 |  | 0%
5.0 | Browser runtime |  |  |  | Not Started |  | Standalone browser product work after export law is fully green. | 10%
5.1 | WebView2 shell and windowing |  |  |  | Not Started |  | 0 | 0%
5.2 | Privacy defaults (tracker blocking / HTTPS-first / safe defaults) |  |  |  | Not Started | 5.1 |  | 0%
5.3 | VPN state / policy integration points |  |  |  | Not Started | 5.1 |  | 0%
5.4 | Session export UX in browser |  |  |  | Not Started | 3.1,5.1 | User-facing export button/command wired to packet generation. | 0%
6.0 | Schemas and policy packs |  |  |  | Not Started |  | 0 | 0%
6.1 | Session transcript schema |  |  |  | Not Started |  | 0 | 0%
6.2 | NFL event schema / duplication rules |  |  |  | Not Started |  | 0 | 0%
6.3 | VPN state schema |  |  |  | Not Started |  | 0 | 0%
6.4 | Canonical / overlay policy packs |  |  |  | Not Started |  | 0 | 0%
7.0 | Quality / release |  |  |  | Not Started |  | 0 | 0%
7.1 | Deterministic runner on clean machine |  |  |  | In Progress | 2.0,3.0 | Must run from scratch with no manual editing and no false GREEN banners. | 50%
7.2 | Regression tests and golden vectors |  |  |  | In Progress | 2.4 | Minimal vector exists; expand coverage after core runner is fully green. | 40%
7.3 | Installer / packaging |  |  |  | Not Started | 5.0,7.1 |  | 0%
7.4 | Release checklist and signoff |  |  |  | Not Started | 7.1,7.2,7.3 |  | 0%

## DoD
Recognition Definition of Done
Area | Definition of Done
Project to spec | Recognition operates as a standalone Windows-first privacy browser with governed, exportable evidence artifacts and no dependency on external engines for the core export law.
Export law | recognition_export_session_packet_v1.ps1 creates a packet from session_export data using default and explicit paths.
Verification | pc_verify_packet_optionA_v1.ps1 verifies exported packets with no manual edits.
Determinism | PacketId is deterministic for identical payload content and canonical manifest bytes.
Selftest | _selftest_packet_constitution_v1.ps1 passes from a clean shell and keeps the minimal golden vector coherent.
Runner hygiene | A single clean runner patches or installs scripts without false GREEN banners or interactive continuation hazards.
Quality gates | All key scripts parse-gate cleanly before execution.
Product readiness | Browser shell, privacy defaults, policy packs, and release checklist are complete for target release.

## Environment
Recognition Instrument Environment
Item | Current canonical value
Repo root | C:\dev\recognition
OS / shell | Windows PowerShell 5.1 workflow assumed
Key scripts directory | scripts\\
Scratch scripts directory | scripts\_scratch\\
Current green milestone | Direct export + verify green; selftest has also been green after targeted fixes.
Immediate remaining gap | One fully clean deterministic runner/install path and final program-level packaging.
Default session export input | payload\session_export
Default packet output | packets\outbox